## Version Control
Document Information
| Document Title | #NAME? | Document No. | #NAME?
| Document Owner | #NAME? | Version No. | #NAME?
| Document Approver | #NAME? | Version Date | 2018-02-02
| Department | #NAME? | Classification | Internal Use
Version History
Version No. | Version Date | Change Description | Prepared By | Approved By
1 | 2018-02-02 | Initial version | Vimala Pradaga
1 | 2018-02-14 | Final Version | Vimala Pradaga
© WHISHWORKS 2016
Copyright: No part of this volume may be reproduced or transmitted in any form or by any means electronic or mechanical including photocopying and recording or by any information storage or retrieval system except as may be expressly permitted by WHISHWORKS

## Summary
Internal - Bugs Summary
New: | 8 | **N/A and Future Release defects are removed from the Total number of defects summarized.
Closed: | 0
Reopened: | 0
Open/In-progress: | 0 | N/A | 0
Fixed: | 0 | Future Release | 0
Net Total Defects: | 8
External - Defects Summary
New: | 0 | **N/A and Future Release defects are removed from the Total number of defects summarized.
Closed: | 10
Reopened: | 0
Open/In-progress: | 0 | N/A | 0
Fixed: | 0 | Future Release | 0
Net Total Defects: | 10

## Sheet1 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1 | Mule Exception if the mandatory element is removed from reservation request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
2 | Mule Exception if the mandatory element is removed from booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
3 | Mule Exception if the mandatory element is removed from cancel-booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
10 | BOIPI-13 -quotes missing in response json | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
5 | Http code 500 with no response in booking is sent from bb-system-api, if mandatory data is not set. | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
6 | Fault is not handled from ECR in bb-system-api | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
9 | If the product category and productDimesionUID is not found during booking then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
8 | If the product category and productDimesionUID is not found during reservation then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19

## Sheet2 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
7 | Nullpointer exception when productDimesionUID and price is not found in cache, this happens in bb-process-api. | Development |  | Developer | 2017-01-09 | Code | Medium | Closed | Archana | 2017-01-10
4 | "Unexpected character" response in cancel-booking of bb-gyg-api if the bookingReference is invalid. | Development |  | Developer | 2017-01-09 | Code | Medium | Closed | Archana | 2017-01-10

## Sheet3 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1 | Mule Exception if the mandatory element is removed from reservation request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
2 | Mule Exception if the mandatory element is removed from booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
3 | Mule Exception if the mandatory element is removed from cancel-booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
5 | Http code 500 with no response in booking is sent from bb-system-api, if mandatory data is not set. | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
6 | Fault is not handled from ECR in bb-system-api | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
8 | If the product category and productDimesionUID is not found during reservation then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
9 | If the product category and productDimesionUID is not found during booking then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
10 | BOIPI-13 -quotes missing in response json | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
4 | "Unexpected character" response in cancel-booking of bb-gyg-api if the bookingReference is invalid. | Development |  | Developer | 2017-01-09 | Code | Medium | Closed | Archana | 2017-01-10
7 | Nullpointer exception when productDimesionUID and price is not found in cache, this happens in bb-process-api. | Development |  | Developer | 2017-01-09 | Code | Medium | Closed | Archana | 2017-01-10

## Sheet4 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1 | Mule Exception if the mandatory element is removed from reservation request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
2 | Mule Exception if the mandatory element is removed from booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
3 | Mule Exception if the mandatory element is removed from cancel-booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
5 | Http code 500 with no response in booking is sent from bb-system-api, if mandatory data is not set. | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
6 | Fault is not handled from ECR in bb-system-api | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
8 | If the product category and productDimesionUID is not found during reservation then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
9 | If the product category and productDimesionUID is not found during booking then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
10 | BOIPI-13 -quotes missing in response json | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
4 | "Unexpected character" response in cancel-booking of bb-gyg-api if the bookingReference is invalid. | Development |  | Developer | 2017-01-09 | Code | Medium | Closed | Archana | 2017-01-10
7 | Nullpointer exception when productDimesionUID and price is not found in cache, this happens in bb-process-api. | Development |  | Developer | 2017-01-09 | Code | Medium | Closed | Archana | 2017-01-10

## Sheet5 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution

## Sheet6 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution

## Sheet7 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1
2
3
4

## Sheet8 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution

## Sheet9 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution

## Sheet10 (hidden)
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1 | Mule Exception if the mandatory element is removed from reservation request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
2 | Mule Exception if the mandatory element is removed from booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
3 | Mule Exception if the mandatory element is removed from cancel-booking request in bb-gyg-api. | Development |  | Developer | 2017-01-06 | Code | High | Closed | Archana | 2017-01-09
10 | BOIPI-13 -quotes missing in response json | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
5 | Http code 500 with no response in booking is sent from bb-system-api, if mandatory data is not set. | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
6 | Fault is not handled from ECR in bb-system-api | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-10
9 | If the product category and productDimesionUID is not found during booking then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19
8 | If the product category and productDimesionUID is not found during reservation then getting exception. This should be a proper error response to consumer | Development |  | Developer | 2017-01-09 | Code | High | Closed | Govind | 2017-01-19

## Analysis (hidden)
Defect Tracking Analysis
Note: Please don't delete any rows from this sheet

## Internal
BugsTracking Log
Project Name | Big Bus Viator Integration |  |  |  |  | Internal Tester: | Vimala Pradaga
Defect # | Defect Description | Service Name | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1 | Service is running properly when we provide empty value to mandatory fields ResellerId,SupplierId and Timestamp from the request. | TourList,Bookings,CancelBookings | Development |  | Tester | 2018-02-02 | Code | High | New | Ramesh
2 | Error messages and error codes are not displaying properly.When we miss mandatory fields the service is throwing "Bad request" as error message and 400 as error code. | TourList,Bookings,CancelBookings | Development |  | Tester | 2018-02-02 | Code | Medium | New | Ramesh
3 | When we are missing mandatory field Apikey value from the request the service is throwing improper error message as "unable to process product list". | TourList | Development |  | Tester | 2018-02-02 | Code | Medium | New | Ramesh
4 | As per the design document the Error and ErrorCode values are not populated under RequestStatus node for the response with status as Error. | TourList | Development |  | Tester | 2018-02-02 | Code | High | New | Ramesh
5 | TourDescription field is missing from the response which is mentioned as mandatory field in design document. | TourList | Development |  | Tester | 2018-02-02 | Code | High | New | Ramesh
6 | Service is running properly when we provide empty value to mandatory fields TravellerIdentifier,GivenName,Surname and AgeBand. | Bookings | Development |  | Tester | 2018-02-02 | Code | High | New | Ramesh
7 | TravellerIdentifier field is missing from the response which is mentioned as mandatory field in design document. | Bookings | Development |  | Tester | 2018-02-02 | Code | High | New | Ramesh
8 | Service is running properly when we provide empty value to mandatory fields BookingReference,CancelDate,Author and Reason. | cancel booking | Development |  | Tester | 2018-02-02 | Code | High | New | Ramesh

## External
Defect Tracking Log
Project Name | BigBus Viator Integration |  |  |  | External Tester:
Defect # | Defect Description | Detected Phase | Area or Deliverable | Detected by | Detected Date | Defect Type | Priority | Status | Assigned to | Resolution Date | Resolution
1 | Viator “Timestamp” format in TourList | UAT |  | Viator Testing Team | 2018-02-16 | Code | Low | Closed | Ramesh | 2018-02-16 | Defect This is happening as we are validating TimeStamp as per the format mentioned in request and response payload samples on Viator Supplier API Tools site ('http://supplierapitestharness.viatorinc.com/api_test_json.php?test=JSON%20Tour%20List')
2 | DeltaOnly' attribute value we considered as String but it's been passed as Boolean - Availability | UAT |  | Viator Testing Team | 2018-02-16 | Code | Low | Closed | Ramesh | 2018-02-16 | Defect
3 | remove the attribute "TourOption": [] in response as there is no data to display - TourList | UAT |  | Viator Testing Team | 2018-02-19 | Code | Low | Closed | Ramesh | 2018-02-19 | This is a request from Viator that they want WW to remove TourOption.WW team kept it for future purpose.
4 | remove "Error": {} element when the "Status" is SUCCESS | UAT |  | Viator Testing Team | 2018-02-19 | Code | Low | Closed | Ramesh | 2018-02-19
5 | remove "UnavailabilityReason" element when the product status is available. | UAT |  | Viator Testing Team | 2018-02-19 | Code | Low | Closed | Ramesh | 2018-02-19
6 | remove QuestionAnswer and QuestionText validations as both are optional. | UAT |  | Viator Testing Team | 2018-02-19 | Requirements | Low | Closed | Ramesh | 2018-02-19 | Requirements are not clear.So, as per the defect description made the fields as optional.
7 | Time Stamp values are not displaying in response as expected. | UAT |  | Viator Testing Team | 2018-02-20 | Code | Low | Closed | Ramesh | 2018-02-20 | Defect
8 | Question element is mapped as string value element in request where it is a string array actually contains question answer and question text. | UAT |  | Viator Testing Team | 2018-02-20 | Change of Scope | Low | Closed | Ramesh | 2018-02-20 | this is not part of our agreed upon field mappings as part of our design
9 | Hitting booking service with proper request payload leads to Internal Error | UAT |  | Viator Testing Team | 2018-02-22 | Code | Low | Closed | Ramesh | 2018-02-22 | missing some value in payload.Cloudhub issue
10 | structural error for traveller array.Extra braces are coming in response. | UAT |  | Viator Testing Team | 2018-02-22 | Code | Low | Closed | Ramesh